## Slide 1
A Look Into the Next-Gen Business Case for HR / Work Technology
A template for securing funding
Ask
Anything
Effective 23 January 2024
Resource created by:

## Slide 2
Business Case Components
    The problem we are trying to solve
    What the problem is costing our business
    The solution to the problem
    Our plan for change management
    Realistic return on investment

## Slide 3
The Problem Overview
Current state:
    Straight-forward, specific, and data-driven.
    Clarifies how it impacts needs/pains of key stakeholders (reference Stakeholder Needs Analysis in Appendix). This creates awareness early on of the problem with leadership, includes their voice in the solution, and reduces the barrier for buy-in.
    Demonstrates how the problem is strategically aligned with organizational goals.
    Clearly shares the results of your evaluation of the current state, identifying gaps & limitations.
    Actionable
Cost / Risk of problem to the business
    Your C-suite needs hard numbers to see how this problem is impacting the business.
    Indicate the cost and risk to the organization if the problem is not addressed.
    Use data obtained from stakeholder analysis feedback to help inform the problem's cost.

## Slide 4
Current state:
    Our HR business partners (HRBP) spend 1-2 hours a day answering employee questions that are sent to them directly in Slack or email.
    As an HR team, we are struggling to get the time to complete the performance review process and launch the new compensation program for 2024.
    We need a way to be able to scale so that we do not have to add more headcount to HR to support employee needs.
Cost/Risk of problem to the business:
    1-2 hours of HR time per day costs the company $258,000 a year.
    Employees may have to wait 24-72 hours to get a response as we do not have the capacity to respond 24/7.
    Often, this negatively impacts the employee's view of the company.
    We need a way to keep our responses to employees consistent, so that we do not have any mis-information that can result in Employee Relations issues.
The Problem - Example

## Slide 5
The Solution Overview
Proposed solution:
    Write a clear solution statement.
    Use data and stakeholder feedback as compelling justifications for the solution.
    Note a clear path to solving the problem.
    Paint a clear picture of the future desired state.

## Slide 6
The Solution (continued)
ROI of solution to the business:
    Focus on realistic and achievable (don’t overpromise).
    Justify the business need by showcasing the benefits that far outweigh the initial investment.
    Compare solution to the cost of doing nothing.
    Address questions on costs, savings, shedding light on implementation costs, licensing fees, training investments, and integration time.
    Quantify benefits, such as enhanced reporting, streamlined processes, and improved employee experience.
    Tangible savings calculation: Calculate tangible time and cost savings achievable through the solution, such as automation.
    Indicate benefits anticipated for each stakeholder.

## Slide 7
The Proposed Solution - Example
Proposed solution:
    To address the aforementioned challenges, we propose the implementation of an Employee Self-Service (ESS) Portal, leveraging advanced HR technology and automation.
Justifications:
    Efficiency Gains: The ESS Portal will empower employees to find answers to common queries without HRBP intervention, significantly reducing the daily 1-2 hours spent. This translates into a direct cost savings of $258,000 annually.
    24/7 Accessibility: The portal will provide employees with round-the-clock access to information, removing the 24-72-hour response time. This not only enhances employee satisfaction but also aligns with modern workplace expectations.
    Consistency and Accuracy: By centralizing information on the ESS Portal, we ensure consistent and accurate responses, mitigating the risk of misinformation and potential Employee Relations issues.
    Data-Driven Decision Making: The portal will generate valuable data on frequently-asked questions, allowing HR to make informed decisions on process improvements, training needs, and addressing common concerns.

## Slide 8
The Proposed Solution - Example
Continued:
  Path to Implementation:
    Assessment and Customization: Conduct a thorough analysis of common employee queries to tailor the ESS Portal to address specific organizational needs.
    Technology Integration: Collaborate with IT to integrate the ESS Portal with existing HR systems, ensuring seamless data flow and real-time updates.
    Stakeholder Training: Provide comprehensive training for HRBPs, employees, and managers to facilitate a smooth transition and maximize the benefits of the ESS Portal
    Monitoring and Iteration: Establish a monitoring system to track the portal's effectiveness and gather feedback for continuous improvement.
  Future Desired State:
    Envision a future where HRBPs dedicate their time to strategic initiatives, such as the performance review process and compensation program launch, unburdened by daily operational queries. Employees experience prompt and accurate responses through the ESS Portal, fostering a positive perception of the company. The organization, equipped with data-driven insights, achieves optimal HR efficiency without the need for additional headcount.

## Slide 9
The ROI Solution - Example
ROI of solution to the business:
    The proposed ESS Portal is designed with practicality and achievability in mind. The anticipated benefits are based on industry benchmarks and realistic expectations, avoiding overpromising and making sure a reasonable implementation.
    The benefits of implementing the ESS Portal far outweigh the initial investment. By significantly reducing HRBPs' daily workload, the organization stands to achieve substantial cost savings, improved efficiency, and enhanced employee satisfaction.
    Choosing to maintain the status quo incurs ongoing costs, including the $258,000 annually for HRBPs' time spent on daily operational queries. The cost of potential Employee Relations issues due to inconsistent responses and delayed communication further adds to the intangible expenses. Implementing the ESS Portal offers a strategic alternative with a clear cost advantage.
  Questions on Costs:
    Implementation Costs: Initial implementation costs will include software development, customization, and integration efforts. A thorough assessment will be conducted to ensure cost-effectiveness.

## Slide 10
The ROI Solution - Example
Continued:
  Questions on Cost
    Licensing Fees: Licensing fees for the ESS Portal software will be factored into the overall investment. Negotiations with vendors will be pursued to secure favorable terms.
    Training Investments: Training costs for HRBPs, employees, and managers will be incurred. However, these investments are crucial for a successful transition and will be justified by the subsequent efficiency gains.
    Integration Time: Collaborating with IT, integration time will be minimized to ensure a swift and seamless connection between the ESS Portal and existing HR systems.
  Quantifying Benefits
    Enhanced Reporting: The ESS Portal will generate detailed reports on frequently asked questions, enabling data-driven decision-making. This enhances HR's ability to identify trends, address common concerns, and optimize processes.
    Streamlined Processes: Automation through the ESS Portal will significantly reduce the time HRBPs spend on operational queries, leading to tangible time savings. This time can then be redirected towards strategic initiatives, such as the performance review process and the new compensation program launch.
.

## Slide 11
The ROI Solution - Example
Continued:
  Quantifying Benefits
    Improved Employee Experience: Employees will benefit from 24/7 access to information, prompt responses, and consistent communication. This positively impacts their perception of the company, fostering a healthier work environment.
  Tangible Savings Calculation:
    Time Savings: Assuming a conservative estimate of 1 hour daily saved per HRBP, the organization stands to save around 260 hours annually per HRBP.
    Cost Savings: At an average HRBP hourly rate of $50, the annual cost savings per HRBP amounts to $13,000. For a team of 10 HRBPs, this translates to a total annual cost saving of $130,000.
  Anticipated Benefits for Each Stakeholder:
    HRBPs: Experience reduced workload, allowing them to focus on strategic initiatives. Job satisfaction is likely to increase as they engage in more meaningful and impactful work.
    Employees: Enjoy improved access to information, faster response times, and a more consistent communication experience, leading to enhanced satisfaction and engagement.
    Organization: Achieves cost savings, operational efficiency, and a positive employer brand. The ability to make informed decisions based on data-driven insights contributes to long-term organizational success.

## Slide 12
Why Now?
4 Use Cases:
  Time Liberation
    Current state: HRBPs spend 1-2 hours daily on direct employee queries.
    Challenge: This operational burden impedes our ability to focus on strategic initiatives.
    Why Now: The ESS Portal unlocks significant time savings for HRBPs, enabling them to redirect their efforts towards high-impact tasks like the performance review process and the new compensation program for 2024.
  Scalability Imperative
    Current state: Increased demand for HR services raises concerns about scalability without adding more headcount.
    Challenge: Without a scalable solution, the risk of overburdened HR resources looms large.
    Why Now: Implementing the ESS Portal is a proactive step towards scalability, ensuring that our HR operations can efficiently accommodate growth without the need for additional staff.

## Slide 13
Why Now?
4 Use Cases - Continued
  Legal Compliance Assurance
    Current State: Inconsistencies in responses pose a risk of misinformation,‌ leading to Employee Relations issues.
    Challenge: Maintaining compliance and consistency in communication is crucial for legal risk mitigation.
    Why Now: The ESS Portal establishes a standardized communication platform, reducing the risk of misinformation and enhancing legal compliance, making it a timely investment.
  Productivity Enhancement
    Current state: Delayed responses impact employee satisfaction and hinder overall productivity.
    Challenge: A less responsive HR communication model affects the organization's productivity and employee morale.
    Why Now: The ESS Portal, with its 24/7 accessibility and streamlined processes, ensures prompt responses, fostering an environment of increased productivity and positive employee experience.

## Slide 14
Change Management
5 Components
  Project Resource Commitments & Impacts
    Who will be working on this project. What is the impact it will have on the people ops team (time and resources). Clarify who the executive sponsor is.
  Project Plan Timeline
    How you plan to roll this out?
    The project plan including proposed timeline of project steps
  Adoption
    How will you get the team to adopt the solution
    The adoption plan
    Now how this plan is reasonable & achievable
  Communication Plan
    Identify the communication plan to support each step of the plan.
    Tailor messages for diverse stakeholder groups, understanding their priorities, concerns, and communication preferences.
  Project Governance
    Indicate how progress will be reported on project plan and adoption.

## Slide 15
RESOURCE | TIME COMMITMENT | IMPACT
Project Manager | Moderate | Oversees entire project, ensures timelines are met
HR Business Partners | High initially, reduced later | Subject Matter Experts, active during customization and training
IT Support | Moderate | Involved in integration and ongoing support
People Operations | Initial High-Time commitment during Implementation; Temporary Shift in Work Priorities | Liberating time for HRBPs, Skill development through training, improvement operational efficience
Change Management - Examples
Project Resource Commitments & Impacts
How are they going to do this project? What is the impact it will have on the people-ops team (time and resources)?

## Slide 16
Change Management - Examples
Project Plan Timeline
Internal Testing
Project Kickoff
Launch to all employees
Ongoing Training and support
Project – Configuration Project – x – x
US – HR
Other countries
Nov. 8-Nov. 21
Testing, training and install
Oct 2, 2023
Oct. 23
Nov. 30
202x
Project Complete
Nov. 1
Launch and ongoing training/adoption

## Slide 17
Change Management - Example
Adoption Plan
  Communication Strategy
    Develop a clear and concise communication plan to inform all stakeholders about the ESS Portal.
    Use multiple channels, including email, town hall meetings, and intranet announcements.
    Highlight the benefits and positive impact on daily operations.
  Stakeholder Engagement
    Identify key stakeholders, including HRBPs, employees, and managers.
    Conduct awareness sessions to showcase the features and advantages of the ESS Portal.
    Address any concerns and gather feedback to enhance the adoption process
  Training Programs
    Customize training programs for different user groups, tailoring content to their specific needs.
    Offer a variety of training formats, including in-person sessions, webinars, and self-paced modules.
    Provide ongoing support through FAQs, user guides, and helpdesk services.

## Slide 18
Change Management - Example
Adoption Plan - Continued
  Pilot Program
    Initiate a pilot program with a select group of users to test the functionality and gather feedback.
    Identify and address any issues or concerns raised during the pilot phase.
    Use insights from the pilot to optimize the system for full-scale implementation.
  Rollout Phases
    Implement the ESS Portal in planned phases to manage the transition effectively.
    Start with a controlled rollout in specific departments or teams.
    Gradually expand the implementation to the entire organization based on feedback and performance.
  Feedback Mechanism
    Establish a robust feedback mechanism to capture user experiences and identify areas for improvement.
    Regularly solicit feedback through surveys, focus groups, and user forums.
    Use feedback to make continuous enhancements to the ESS Portal.

## Slide 19
Change Management - Example
Adoption Plan - Continued
  Recognition & Rewards
    Recognize and reward early adopters and contributors to the success of the ESS Portal.
    Highlight positive stories and testimonials to encourage broader adoption.
    Foster a culture of appreciation for those embracing the new system.

## Slide 20
Change Management - Example
Communication Plan
  Objective Statement
    Provide effective communication throughout the ESS Portal project.
  Stakeholders
    Executives, Steering Committee, Project Teams, HRBPs, Employees, IT.
  Channels & Frequency
    Weekly Email Updates - Weekly progress emails with key updates.
    Monthly Town Hall Meetings - Regular announcements highlighting portal features.
    Ongoing Intranet Announcements - Bi-weekly feature highlights.
  Key Messages
    Benefits of ESS Portal Implementation, such as Time savings for HRBPs. 24/7 access for employees.
    Project milestones and progress updates.
    Impact on Daily Operations and Employee Experience, such as Improved communication consistency for employees.
  Responsibility
    Project Manager oversees content, team manages delivery.

## Slide 21
Change Management - Example
Communication Plan - Continued
  Feedback Mechanism(s)
    Monthly surveys on communication effectiveness.
    Quarterly town hall Q&A sessions.
    Monthly committee meetings for input and guidance.
  Escalation Process
    Project Manager for daily updates or as needed for urgent matters.
    Monthly committee meetings for strategic discussions.
    Dedicated Helpdesk for Employee Queries.
  Timeline
    Monthly committee meetings for strategic discussions.

## Slide 22
Change Management - Example
Project Governance
  Steering Committe
    Establish a Steering Committee consisting of key executives, project sponsors, and relevant stakeholders. Define their role in providing strategic oversight, decision-making, and alignment with organizational goals. Hold regular Steering Committee meetings to review project progress and address strategic concerns.
  Project Manager
    Appoint a dedicated Project Manager responsible for day-to-day oversight and coordination. Make sure the Project Manager serves as the central point of communication between different project teams. Empower the Project Manager with decision-making authority within defined parameters.
  Project Team
    Form cross-functional project teams, including HR, IT, Training, and Communication teams. Clearly define the responsibilities and objectives of each team. Foster collaboration and communication among teams to provide a unified approach.
  Risk Management
    Establish a risk management plan to identify, assess, and mitigate potential project risks. Define escalation paths for addressing high-impact risks. Regularly review and update the risk management plan to adapt to evolving project dynamics.

## Slide 23
Change Management - Example
Project Governance - Continued
  Change Control Process
    Implement a change control process to manage any modifications to the project scope or objectives. Clearly define the criteria for evaluating and approving change requests. Make sure changes are communicated effectively to all stakeholders.
  Milestone Tracking
    Implement a milestone tracking system to track project progress. Define key milestones and timelines for each phase of the project. Regularly update stakeholders on milestone achievements and potential deviations.
  Performance Metrics
    Define performance metrics aligned with project objectives. Regularly assess and report on key performance indicators (KPIs) to measure project success. Use performance metrics to inform decision-making and continuous improvement efforts.

## Slide 24
Appendix A
Stakeholder Needs Analysis
Stakeholder Role | Identify Needs & Painpoints | Solutions Alignment | Cost to Business IF Not Addresses
List key stakeholders and their roles in the decision-making process. Listen and include them in the design of the solution. Helps reduce buy in barriers later. Feedback gathered also helps identify communication change management plan needs. | Analyze the challenges and pain points of stakeholders through interviews and feedback. | Demonstrate how HR AI technology addresses identified needs and aligns with organizational goals. | List cost (numerical value if possible) to the business if needs/pains are not addressed. Indicate level of risk.

## Slide 25
STRENGTHS | WEAKNESSES
OPPORTUNITIES | THREATS
Appendix B
SWOT Exploration of Chosen Solution
Provides an understanding of the risks associated with the solution. Identifies assumptions and risks of solutions. Clarify how this solution compared to others you considered in the RFP process (consider research, vendor evaluations, reviews, and product demos). Consider not just the immediate benefits but the long-term value of the solution in comparison to others. Clarify why this solution is the best Include Key Stakeholder Feedback Note you may move this to the appendix but speak to it in your solution statement & ROI calculation.

## Slide 26
About MeBeBot
  SasS Solution, with AI Chatbot and Customer Portal for Employee Experience
  Adopted by employees in 50+ countries
  Focus on automation of employees' FAQs, push messaging, pulse surveys and data
  Award-winning solution, including “Brilliant Bot” selection in Slack App Marketplace
  Five Star reviews on G2 and Top 11 HR Chatbots on Select Software Reviews
  100% customer renewals

## Slide 27
Contact Us
info@mebebot.com
(726) 999-0151
https://www.mebebot.com
https://www.linkedin.com/company/mebebot
@HRTalkBot
https://www.facebook.com/mebebot.chatbots